## Data Dictionary
# | Submitter & date | BHDC DD Reference | Tier 1, 2 or 3 (change control) | Who needs to Address (DBHR added) | Recommendation/Issue/Question from the RSN/BHOs | DBHR Decision | Reasoning/Clarification | Response from Submitter | Action Needed | Status
1 | Danielle Repp <drepp@co.kitsap.wa.us>, 2016-2-5 | ASAM |  | Michael Davis | 2016-2-5: In the Summary of Transactions table it shows that the ASAM transaction is required for both Mental Health and SUD. | agree |  |  | change language to make mandatory only for SUD, optional for MH | change(s)/response accepted by DBHR and change(s)/response pending
2 | Michael S. White [mailto:michael_white@nsmha.org] 2016-01-28 | Episode Modalities |  | Michael Davis | 2016-01-28: The Definition and Edits sections on page 22 do not speak to whether it is DBHRs intention that with each change in Service Episode Modality whether or not there is expected to get a new Service Episode record for each change. Yet the definitions for the Service Episode Start Date and Service Episode End Date definitions indicate this is the case. Can you please clarify? Can you also provide some background as to why this was added please? | 2016-1-28: One thing that we've learned from TARGET is that "optional" data elements end up being fairly useless. A new episode transaction needs to be entered whenever modality changes. Requiring modality is one way to ensure that happens, and it is really important that separate transactions are entered when a modality changes - even at the same provider. I don't see any explanation as to why modality cannot be provided. | 2016-1-28: If we drop it, we'll be able to figure out when providers are not entering new episode transactions when modalities change (through efforts to link P1 service data to transaction data) and alert BHOs to the errors but asking for modality will likely minimize those data entry errors. |  | possibly add language to ensure a new episode is created when modality changes | awaiting decision on change(s)/response
3 | Pickens-Rucker, Kathy (HCA) [mailto:kathy.pickens-rucker@hca.wa.gov] 2016-1-28 | Episode Modalities |  | Michael Davis | 2016-1-28: The addition of service episode "modality" is problematic in SW. Additional discussion would be appreciated. | refer to Katie Weaver Randall's response to this topic, if questions still exist then please e-mail DSHS BHDC Project (DSHS) at bhdcproject@dshs.wa.gov |  |  |  | awaiting decision on change(s)/response
4 | Creighton, Nancy [mailto:Nancy.Creighton@kingcounty.gov] 2016-01-28 | Episode Modalities |  | Michael Davis | 2016-01-28: The level of detail expected on the SUD side (all "modalities" using the TARGET term, which is substantially ASAM level) compared to just "MH" on the mental health side is puzzling (and problematic for King BHO). 2016-2-3: Just out of curiosity, where did you see "modality" in the Service Episode transaction before this "final" data dictionary. The last draft version (from December 2015) that I have, had not just no "modality" but also no indicator even of whether or not it was for MH or SUD - which we thoughtfully pointed out to DBHR, then they went a little crazy (unless I've lost my mind). | refer to Katie Weaver Randall's response to this topic, if questions still exist then please e-mail DSHS BHDC Project (DSHS) at bhdcproject@dshs.wa.gov |  |  |  | awaiting decision on change(s)/response
5 | Bruce Waddell (SP RSN), 2016-2-3 | Episode Modalities |  | Michael Davis | 2016-2-3: The expanded Episode Modality will create a great deal of headache and additional work for Spokane BHO and our providers. We would support having a SUD OP and SUD IP service modality, but to have a modality for all of these different categories doesn't seem necessary. | refer to Katie Weaver Randall's response to this topic, if questions still exist then please e-mail DSHS BHDC Project (DSHS) at bhdcproject@dshs.wa.gov |  |  |  | awaiting decision on change(s)/response
6 | Mcdowell, Gerene F [mailto:gerene.mcdowell@optum.com] 2016-2-3 | Episode Modalities |  | Michael Davis | 2016-2-3: While we agree the expanded Episode Modality does create difficulty and extra work, and we don't agree with this being placed in the Service Episode vs. the Authorization transaction, we understood this was a requirement and it was a 'final' decision for at least six to twelve months. Therefore, we (three) future BHOs have moved ahead with the extra time and expense in modifying and testing software, so we do hope at a minimum the service modality will be accepted (even if not required) as documented in the final version of the BHD Final Reporting Guide. 2016-2-4: I am sure I am guilty for bringing up the question on how they planned to tell SUD OP from SUD IP, but we never asked for this level of detail and I understood from the meeting, no decision had been made. This will be a huge change in our design and a great deal of extra work for our underfunded providers. | agree | SUD inpatient is not an option in other systems we use |  | remove SUD Inpatient code from modality table | change(s)/response accepted by DBHR and change(s)/response pending
7 | Michael Davis 2016-2-9 |  |  | DBHR | 2016-2-9: Option 3 is “No requirement around which BHO reports (service BHO or responsible BHO), but each BHO works it out with their providers and other BHOs to ensure that all service encounters are reported through Provider One.” I just want to ensure the statement is correct, or was it intended to say “ensure that all service encounters are reported as per the BHDC Data Dictionary”? Using the BHDC Data Dictionary would make sense because it would force BHOs to start a new episode when the modality changes. Otherwise, I assume Provider One is in the language because DSE will link non-P1 data to P1 in order to determine the modality. | 2016-2-9 Katie: I am looking at this. I need to re-familiarize myself with the service episode transaction and how it will/will not interact with the encounter reporting. 2016-2-9 Kevin: Or “all service encounters are reported through Provider One and related service information is reported as per the BHDC Data Dictionary (e.g., service episode transactions, client demographics, etc.).” --> We just don’t want them to think that options 3 only requires them to report into P1. We still need all the associated non-P1 information in the BHDC. |  |  | add: ALSO MUST report associated information through non-P1 system/transactions | change(s)/response accepted by DBHR and change(s)/response pending
8 | Stan, Kowalkowski 2016-2-9 | Substances |  | Stan Kowalkowski | 2016-2-9: BHOs probably do need to collect the three SUD substances for the prior admit, because: the BHDC DD says: “The same substance(s) must be included in the report at admission, every 90 days, and at discharge. The purpose of this is to detect how frequency and method of use change for the 3 substances between admission and discharge. “ Second note – it is not clear to me, from this wording, that the same primary substance must be carried forward for the Periodic and Discharge updates – are we going to allow a change between Primary, Secondary, and Tertiary as long as the same three substances reported at Admit, are reported on in the Periodic and in the Discharge updates? | need to maintain order of substances | order of substances reflects order of importance, which for DBHR's purposes cannot be changing through the episode while tracking the change in aspects of those substances |  | add language to make sure that the order of importance does not change from the order presented at admission | change(s)/response accepted by DBHR and change(s)/response pending
9 | Pickens-Rucker, Kathy (HCA) [mailto:kathy.pickens-rucker@hca.wa.gov] 2016-2-2 | Episode Modalities |  | Michael Davis | 2016--2-2: We are not going to be able to require our MCOs/ASO in SW to submit the “modalities” that were an added data element in the 1/19/16 version of the dictionary. I just need confirmation it won’t be a problem if we leave this field blank. | refer to Katie Weaver Randall's response to this topic, if questions still exist then please e-mail DSHS BHDC Project (DSHS) at bhdcproject@dshs.wa.gov |  |  |  | awaiting decision on change(s)/response
10 | Pickens-Rucker, Kathy (HCA) [mailto:kathy.pickens-rucker@hca.wa.gov] 2016-2-2 | Client ID |  | DBHR | 2016-2-2: The language on page 101 of the dictionary, regarding “Client ID,” is not clear. Could you confirm that it will be ok for our MCOs/ASO in SW to submit the ProviderOne client ID in the client ID field throughout all the applicable transactions? If it is a non-Medicaid person, the ASO will submit some other unique ID. | ASOs can remove edits to allow non-P1 identifiers in this field, because they require P1 ID and need a way to enter patients who are not in P1 (we are okay accepting that this will affect data quality). |  |  |  | change(s)/response accepted by DBHR and change(s)/response pending
11 | Pickens-Rucker, Kathy (HCA) [mailto:kathy.pickens-rucker@hca.wa.gov] 2016-2-2 | Client ID |  | Tom Cronin and Kevin Campbell | 2016-2-2: Can you clarify what is meant on page 101 by this definition of “Client ID” - A string of characters, in combination with a service entity (BHO, treatment provider, etc.) uniquely identifies a client within the system overseen by the service entity? It sounds like the Client ID is a combination of 2 numbers and you want them both in the “Client ID” field. Some have suggested that “servicing entity” is referring to the “BHO ID” field defined on page 102. We are confused. | Client ID element is purely a unique number assigned by the BHO to each of their clients | language was confusing |  | clarify language to reflect that Client ID field is a unique number assigned to each client by the client's BHO remove language about combinations | change(s)/response accepted by DBHR and change(s)/response pending
12 | Creighton, Nancy <Nancy.Creighton@kingcounty.gov> 2016-1-29 | Episode Modalities |  | DBHR | 2016-1-29: We do not plan to authorize by these SUD modalities for outpatient, but rather to have two broader benefit levels, one of which would apply to IOP and/or OP, and the other to Outpatient at a recovery support level. DBHR requiring this level of detail (IOP vs OP) will require that we pull other data into the process for identifying what to submit in the Service Episode transaction. | agree | SUD inpatient is not an option in other systems we use |  | remove SUD Inpatient code from modality table | change(s)/response accepted by DBHR and change(s)/response pending
13 | Creighton, Nancy <Nancy.Creighton@kingcounty.gov> 2016-1-29 | service episode transaction |  | DSE | 2016-1-29: The service episode transaction still says that it was worked out with RSNs "as the simplest way for RSNs to report outpatient treatment episodes of care" and this part of it (the highly detailed SUD modality list) most certainly wasn't. And, in fact, it says it's about reporting "outpatient treatment episodes of care" but you've just expanded it to all SUD episodes of care. | understood | we did make a change by adding episode modality, but only in an attempt to ensure an episode represents a single modality (those listed) and to ensure we know which modality is being used |  | possibly remove sentence about being worked out with RSNs as the simplest way to report | awaiting decision on change(s)/response
14 | Danielle Repp <drepp@co.kitsap.wa.us> 2016-1-28 | Client Profile |  |  | 2016-1-28: The Client Profile 035.08 should have Effective Date in the Primary Key section. | no, it should be in body | if it were in primary key then a new client would be created each time their profile was collected |  | no action | change(s)/response accepted by DBHR and change(s) made/comments released
15 | Michael Davis 2016-1-25 | Program ID |  | Katie Weaver Randall | 2016-1-25: As the CDDA codes reflect programs that might not be funded by the BHDC, do you anticipate BHO’s will react to request they are removed as an option? | 2016-1-27: I don’t think it will be an issue to remove or add codes to the Program ID list. Removing or adding code values is much less of an issue than removing or adding whole data elements. |  |  | more information from Bob Leonard regarding: remove CDDA and CDAA codes from Program ID | change(s)/response accepted by DBHR and change(s)/response pending
16 | Wu, Ming (HCA) <ming.wu@hca.wa.gov> 2016-1-22 | Posting to DBHR website |  |  | 2016-1-22: Is this document something that will be on the DBHR website? | Yes |  |  | Upload to website | change(s)/response accepted by DBHR and change(s)/response pending

## Error Codes and Reports
# | Submitter & date | Error Reporting Reference | Tier 1, 2 or 3 (change control) | Who needs to Address (DBHR added) | Recommendation/Issue/Question from the RSN/BHOs | DBHR Decision | Reasoning/Clarification | Response from Submitter | Action Needed | Status
1 | Katie Weaver Randall 2016-2-9 | General |  | BHA IT | 2016-2-9: 1. When do we anticipate having this work done? 2. Will this information about error codes need to go into the Data Reporting Guide? If so, when? 3. What from all of this do I need to share with HCA and the MCOs and BHASO in the SW Region? I will be meeting with them on Feb. 22nd so it would be a good opportunity to share any additional information that may impact their data reporting to us. | 2016-2-9: 1. Before Feb 26th 2. No. 3. Likely, they may be interested to know the errors we are capable of detecting for Phase I and that they will receive an error report. | 2016-2-9: 1. Before testing 2. Error codes are based on rules in the Reporting Guide, database limitations and possibly analytical limitations. A error report will likely be automatically generated that is sent to BHOs with the errors they made so they can correct/resend errors. 3. Phase 1 error detection is focused on critical errors that make data unusable. Currently, error types include field errors (improper characters, length, etc.), business errors (violating rules in data dictionary), analytical errors (mostly Phase II, but logical errors that affect analysis). As long as they follow the reporting guide/data dictionary they will not generate errors. |  | no action | change(s)/response accepted by DBHR and change(s) made/comments released
2 | Stan, Kowalkowski 2016-2-9 | Documentation |  |  | 2016-2-9: the BHDC DD is where we would document the transaction errors – it/they are not going to be on every page – just the “Transactions and Definitions” pages ( 9-24) | agree |  |  | 2016-2-9: if determined to place error codes in data dictionary then include with other changes for v1.2 | awaiting decision on change(s)/response

## Testing
# | Submitter & date | BHDC Reference | Tier 1, 2 or 3 (change control) | Who needs to Address (DBHR added) | Recommendation/Issue/Question from the RSN/BHOs | DBHR Decision | Reasoning/Clarification | Response from Submitter | Action Needed | Status
1 | Bruce Waddell (SP RSN), 2/4/2016 |  |  | Jerry Britcher | 2016-2-4: Will we be testing the ability to send both the current transactions for dates prior to 4/1/16 and for the new transactions for dates starting 4/1/16? Since we cannot process future dates, what will be the date that will be used for pre/post 4/1/16? | 2016-2-4: You will have separate SFTP accounts for your current (“RSN”) transactions and for your new Behavioral Health Organization transactions. Any data related to service encounters that occur prior to 4/1/2016 will utilize the RSN account and be submitted to the current CIS/TARGET applications. For service encounters that occur 4/1/2016 or after, these must be submitted using your new BHO account. Testing to begin 2/26/2016 will be for your new BHO account. There should be no changes to your existing account, and transactions will work exactly as they do now. |  | 2106-2-5: Just to clarify, in April if I have a Service episode that started in March but hasn’t been submitted, I send this to the current CIS and if I have a Program record for the same client and episode that started April 7th, I send this to the new system. This makes me think that you are having both of these systems talking to each other in real time. Is this what you meant? For SUD Substances, if the client was admitted and in Target prior to 4/1/16 and still open as of 4/1/16, is there an expectation we will collect the admit SUD Substance and report it even if it was for pre April? If not, will you be accepting change SUD Substance “change” at 90 day interval without the admit SUD Substance? | Awaiting response from DBHR regarding: 2016-2-5: I think his first two statements are correct, but CIS and BHDS will not talk in real time. Is there a reason why the BHOs would want a live update from CIS to BHDS? Also, I don’t know how to answer the SUD questions. | awaiting decision on change(s)/response

## DB Function
# | Submitter & date | DB Function Reference | Tier 1, 2 or 3 (change control) | Who needs to Address (DBHR added) | Recommendation/Issue/Question from the RSN/BHOs | DBHR Decision | Reasoning/Clarification | Response from Submitter | Action Needed | Status
1 | Pickens-Rucker, Kathy (HCA) [mailto:kathy.pickens-rucker@hca.wa.gov] 2016-2-2 | Close Outs |  |  | 2016-2-2: The SW RSN plans to send “close out” transactions for all their records in CIS. Can we tell our MCOs/ASO they need not worry about any history and can just start submitting their files after 4/1/16 as though all clients and services are new? Any guidance on data conversion is much appreciated. | agree |  |  | MCOs/ASO need not worry about any history and can just start submitting their files after 4/1/16 as though all clients and services are new. This is also true for BHOs, they will just start entering new data. We will have the “history” through migration of TARGET and CIS into the new BHDC. | change(s)/response accepted by DBHR and change(s)/response pending

## Reports
# | Submitter & date | BHDC Reference | Who needs to Address (DBHR added) | Recommendation/Issue/Question from the RSN/BHOs | DBHR Decision | Reasoning/Clarification | Response from Submitter | Action Needed | Status
1 | Bruce Waddell (SP RSN), 11/30/2015 | April 2016 Conversion |  | April 2016 Conversion questions: 1. If a client is active on 4/1/16 but the episode was opened prior to 4/1/16 in Target, what is your expectation on the data for these clients records associated with the admission such as SUD Substances, State Data, Co-Occurring, ASAM? a. Does the BHO and State just not have this data for these clients? b. Does the State link to Target for this information? c. Do they need to get this data reassessed and reported as of 4/1/16? 2. For MH client data reported in April 2016 for March 2016 or prior that will be in transactions or data elements that were changed effective 4/1/16, will the current transactions be available for reporting of data if the effective date is prior to 4/1/16? a. If yes, how long will these retired transactions be available? b. If no, what is the plan for data clean up and submission? 3. For MH clients open as of 4/1/16, when will the new transactions be required? Example, Authorization, revised State Data, etc. Missing Required record: Will the state provide reports or feedback when clients are missing required transactions that are due at admission, 90 days or discharge? |  |  |  |  | awaiting decision on change(s)/response
2 | Bruce Waddell (SP RSN), 11/30/2015 | SUD Substance transaction corrections: |  | If the SUD Substance transaction is reported and it is determined that a substance reported is not correct and does not apply to the client, can this record be deleted or changed? |  |  |  |  | awaiting decision on change(s)/response
3 | Bruce Waddell (SP RSN), 10/30/2015 | Missing Required record: |  | Will the state provide reports or feedback when clients are missing required transactions that are due at admission, 90 days or discharge? |  |  |  |  | awaiting decision on change(s)/response
4 | Katie Weaver Randall | Authorized v. not authorized CH claims |  | Authorized v. not authorized CH claims. How to assign RSNs to not authorized claims in the new BHDC system. |  |  |  |  | awaiting decision on change(s)/response
5 | Mcdowell, Gerene OPTUM 12/03/2015 | Summary of Transactions vs. Transactions and Definitions | DAWG | for our development (currently in progress) is which document are we to use for programming the order of the data elements in each transaction? | 2015-12-07: transactions and definitions | definitions are in a logical order and specify the primary keys | 2015-12-07: Gerene was pleased with decision |  | change(s)/response accepted by DBHR and change(s) made/comments released
6 | Pickens-Rucker, Kathy (HCA) [mailto:kathy.pickens-rucker@hca.wa.gov] 2016-2-2 | TARGET | Stan Kowalkowski | 2016-2-2: 1. What is the status of adding the drop down value in TARGET that let’s SUD providers in SW indicate they have received a signed release? SW says they have not been able to enter those yet. 2. When can we expect the draft layout of the planned data extract? |  |  |  |  | awaiting decision on change(s)/response

## Contracts
# | Submitter & date | BHDC/BHO Reference | Tier 1, 2 or 3 (change control) | Who needs to Address (DBHR added) | Recommendation/Issue/Question from the RSN/BHOs | DBHR Decision | Reasoning/Clarification | Response from Submitter | Action Needed | Status
1 | Csendes, Michael [mailto:Michael.Csendes@kingcounty.gov] 2016-01-27 |  |  | David Johnson | 2016-1-27: Do you know the plans for reporting BHO eligibility in ProviderOne? Currently "King County RSN" is listed in the "Managed Care" section of the ProviderOne portal (and in the 834 file). Will this change to "King County BHO"? Will anything change in the 834 file? For example, will the same identifier be used for King County BHO (105020601)? | 2016-2-3: I believe your assumptions are correct. There will be 9 BHOs on April 1st. Only two BHO identifiers will change the other seven will stay the same. (Great Rivers and Thurston Mason BHO will be issued new identifiers as their FEIN’s are changing with new configurations of their fiscal agents.) All other BHO’s continue in much the same fashion--albeit the names will be changed to reflect their statuses as BHOs. |  |  |  | change(s)/response accepted by DBHR and change(s) made/comments released
2 | Danielle Repp <drepp@co.kitsap.wa.us> 2016-2-1 | NPIs |  | David Johnson | 2016-2-1: I see some hospitals on this list that weren’t on the other. |  |  |  |  | awaiting decision on change(s)/response

## General Plan
# | Submitter & date | DB Function Reference | Tier 1, 2 or 3 (change control) | Who needs to Address (DBHR added) | Recommendation/Issue/Question from the RSN/BHOs | DBHR Decision | Reasoning/Clarification | Response from Submitter | Action Needed | Status
1 | Bruce Waddell (SP RSN), 12/2/2015 | State's Data Consolidation Plan (conversion) |  |  | 1. If a client is active on 4/1/16 but the episode was opened prior to 4/1/16 in Target, what is your expectation on the data for these clients records associated with the admission such as SUD Substances, State Data, Co-Occurring, ASAM? a. Does the BHO and State just not have this data for these clients? b. Does the State link to Target for this information? c. Do they need to get this data reassessed and reported as of 4/1/16? | see contracts, communications from Jerry Britcher and Katie Weaver Randall; if questions still exist then please e-mail DSHS BHDC Project (DSHS) at bhdcproject@dshs.wa.gov
2 | Bruce Waddell (SP RSN), 12/2/2015 | State's Data Consolidation Plan (conversion) |  |  | 2. For MH client data reported in April 2016 for March 2016 or prior that will be in transactions or data elements that were changed effective 4/1/16, will the current transactions be available for reporting of data if the effective date is prior to 4/1/16? a. If yes, how long will these retired transactions be available? b. If no, what is the plan for data clean up and submission? | see contracts, communications from Jerry Britcher and Katie Weaver Randall; if questions still exist then please e-mail DSHS BHDC Project (DSHS) at bhdcproject@dshs.wa.gov
3 | Bruce Waddell (SP RSN), 12/2/2015 | State's Data Consolidation Plan (conversion) |  |  | 3. For MH clients open as of 4/1/16, when will the new transactions be required? Example, Authorization, revised State Data, etc. | see contracts, communications from Jerry Britcher and Katie Weaver Randall; if questions still exist then please e-mail DSHS BHDC Project (DSHS) at bhdcproject@dshs.wa.gov
4 | Bruce Waddell (SP RSN), 12/2/2015 | State's Data Consolidation Plan (SUD Transaction) |  |  | If the SUD Substance transaction is reported and it is determined that a substance reported is not correct and does not apply to the client, can this record be deleted or changed? This type of error could be a result of a data entry error or bad information from the client. | see contracts, communications from Jerry Britcher and Katie Weaver Randall; if questions still exist then please e-mail DSHS BHDC Project (DSHS) at bhdcproject@dshs.wa.gov
5 | Bruce Waddell (SP RSN), 12/2/2015 | State's Data Consolidation Plan (completeness report) |  |  | Will the state provide reports or feedback when clients are missing required transactions that are due at admission, 90 days or discharge? | see contracts, communications from Jerry Britcher and Katie Weaver Randall; if questions still exist then please e-mail DSHS BHDC Project (DSHS) at bhdcproject@dshs.wa.gov
6 | Bruce Waddell (SP RSN), 12/23/2015 | State's Data Consolidation Plan (conversion) |  | present with data conversion plan at the 4JAN2015 BHO meeting | 1. Are you building a new Data Collection system or modifying the existing system? 2. What information that we have already submitted will be in the system as of 4/1/16? a. Will the data still be in the format we submitted or in a converted format? 3. For information that is effective prior to 4/1/16 will we be submitting to DBHR using the current transactions or the new transactions? a. If we are going to be required to use the new transactions, will the system allow for the fact that some information was not collected and therefore not available for submission? 4. If we need to change or delete a pre 4/1/16 transaction, how do you plan to allow for this? | see contracts, communications from Jerry Britcher and Katie Weaver Randall; if questions still exist then please e-mail DSHS BHDC Project (DSHS) at bhdcproject@dshs.wa.gov
7 | Bruce Waddell (SP RSN), 12/23/2015 | State's Data Consolidation Plan (transition) |  | present with data conversion plan at the 4JAN2015 BHO meeting | What is the plan and expectation for reporting the new transactions for existing MH and SUD clients? For example: 1. Are all of the SUD clients that are open as of 4/1/16 required to have a full set of data collected and reported in April? 2. For exiting MH clients, how soon do the revised\new transactions have to be submitted to the State? a. (i.e. does this need to occur in April or at the next 90/180/reauthorization period?) | see contracts, communications from Jerry Britcher and Katie Weaver Randall; if questions still exist then please e-mail DSHS BHDC Project (DSHS) at bhdcproject@dshs.wa.gov
8 | Bruce Waddell (SP RSN), 12/23/2015 | State's Data Consolidation Plan (testing) |  | present with data conversion plan at the 4JAN2015 BHO meeting | 1. What is the testing plan and requirements for NATIVE transactions? 2. When will the testing system be ready to process our test files? 3. Will the test system have converted data in it to allow us to do more than just format testing? | 2016-02-10: While testing will be available starting 2/26, the window for testing will extend to March 28. If testing is needed beyond the 3/28 date (including past the 4/1 Go Live), we will need to be notified by COB Tuesday, March 29. |  |  |  | change(s)/response accepted by DBHR and change(s) made/comments released
9 | Bruce Waddell (SP RSN), 12/31/2015 | State's Data Consolidation Plan (testing) |  | present with data conversion plan at the 4JAN2015 BHO meeting | 1. When will the State be able to accept test files? 2. How long will “RSN” data be accepted post-March 31st? 3. When may we expect the spreadsheet of State NPIs (even an incomplete list would be appreciated) | 2016-02-10: While testing will be available starting 2/26, the window for testing will extend to March 28. If testing is needed beyond the 3/28 date (including past the 4/1 Go Live), we will need to be notified by COB Tuesday, March 29. |  |  |  | change(s)/response accepted by DBHR and change(s) made/comments released
10 | Bruce Waddell (SP RSN), 2016-2-3 | Data Transition |  |  | 2016-2-3: We are also wondering about what the plan is for data transition for April 1. | Can start putting new data into BHDC regardless of whether or not you are still inputting data into systems that will be decommission thereafter. |  |  |  | change(s)/response accepted by DBHR and change(s)/response pending
11 | Mcdowell, Gerene F [mailto:gerene.mcdowell@optum.com] 2016-2-3 | Data Transition |  |  | 2016-2-3: Yes, we, too, are anxious to hear the transition plan, and when we may begin testing with the State. | Can start putting new data into BHDC regardless of whether or not you are still inputting data into systems that will be decommission thereafter. |  |  |  | change(s)/response accepted by DBHR and change(s)/response pending
12 | Bruce Waddell (SP RSN), 2016-2-5 |  |  | Katie Weaver-Randall | 2016-2-5: 1. Just to clarify, in April if I have a Service episode that started in March but hasn’t been submitted, I send this to the current CIS and if I have a Program record for the same client and episode that started April 7th, I send this to the new system. 2. This makes me think that you are having both of these systems talking to each other in real time. Is this what you meant? 3. For SUD Substances, if the client was admitted and in Target prior to 4/1/16 and still open as of 4/1/16, is there an expectation we will collect the admit SUD Substance and report it even if it was for pre April? 4. If not, will you be accepting change SUD Substance “change” at 90 day interval without the admit SUD Substance? | 2016-2-9: 1. Correct. 2. DBHR will have a process to link the pre-April 1, 2016 data (CIS or TARGET) to the data that comes in under the new requirements. 3. No. We would not expect you to collect the Admit SUD Substance and report it if it was already reported in TARGET. The same process as described above will be used to link the pre-April 1, 2016 data to the data coming in under the new requirements. In this case, DBHR will identify the admit substance from TARGET and link it to the 90 day updated Substance for that client. 4. Yes, because we will already have the admit substance. |  |  |  | change(s)/response accepted by DBHR and change(s) made/comments released