| **Policy 7.01 Plan**  **Region 3 Developmental Disabilities Administration (DDA) and Hoh Tribe**  **2014-2015 Update** | | | | |
| --- | --- | --- | --- | --- |
| **Implementation Plan** | | | | **Progress Report** |
| **(1) Goals/Objectives** | **(2) Activities** | **(3) Expected Outcome** | **(4) Lead Staff and Target Date** | **(5) Status Update for the Fiscal Year  Starting Last July 1** |
| 1. Ensure the Hoh Tribe has information available for services and support | DDA will meet annually with the Hoh Tribe to schedule a review of the 7.01 Plan.  The designated local DDA liaison will participate in meetings as requested by the Hoh Tribe.  Promote local collaboration between the Hoh Tribe and DDA.  As requested by the Hoh Tribe, DDA staff will provide training and education regarding DDA programs and services.  Participate in weekly staff meetings as requested by the Hoh Tribe. | The Hoh Tribal members will have the opportunity to apply and receive services as Tribal member DDA eligibility is identified | DDA Regional Administrator (RA) and DDA Quality Assurance (QA) Manager  Will meet in:  February 2015  DDA local Tribal  Liaison  Tobias Clawson  Tribal Representatives | DDA and the Hoh Tribe met on 2/4/2014 |
| 2. Provide written information about DDA services to all Tribes at least annually | Region 3 DDA will send a formal letter to the Tribal Chair with copies to the Social Services Director and to the Office of Indian Policy, including:   * Current brochures describing DDA services; * A current list of Region 3 DDA staff designated as Tribal liaisons, including staff telephone numbers and email addresses. | Information about DDA services and local contacts will be available to the Tribe on an ongoing basis. | DDA Regional QA Manager will send out on an annual basis. | Information was shared in the 7.01 meeting on 2/4/2014 the designated Tribal members received updated information including contacts. |
| 3. Facilitate employment opportunities within DDA for Tribal members | DDA will forward job/recruitment announcements electronically to the Hoh Tribe designated representatives | Ongoing opportunity for Hoh Tribal members to apply for DDA positions  Increased diversity within the DDA workforce | DDA Regional Administrative Assistant | Ongoing |
| 4. Promote cultural awareness and sensitivity by all DDA staff | Ensure DDA staff attends Government-to-Government and Centennial Accord training as appropriate.  Participate in cultural sensitivity training offered by the Hoh Tribe  At the request of the Hoh Tribe, DDA liaison will participate in the Annual Tribal Health Fair in May | DDA staff will be available to the Hoh Tribe to learn their history as opportunity and training is provided by the Tribe | Designated Hoh Tribal representatives, local Tribal liaisons, and regional DDA staff | DDA Region 3 is currently assessing training needs for its staff and plans to ensure that needed training occurs in 2014-15 |
| 5. Ensure that the Hoh Tribe is made aware of trainings available through DDA. | DDA will forward training announcements and information electronically to the Tribes designated representatives. | Ongoing opportunities for Tribal members to be aware of and participate in relevant DDA trainings. | QA manager or designee | Ongoing |