| **Policy 7.01 Plan**  **Region 3 Developmental Disabilities Administration (DDA) and Nisqually Indian Tribe**  **2014-2015 Update** | | | | |
| --- | --- | --- | --- | --- |
| **Implementation Plan** | | | | **Progress Report** |
| **(1) Goals/Objectives** | **(2) Activities** | **(3) Expected Outcome** | **(4) Lead Staff and Target Date** | **(5) Status Update for the Fiscal Year  Starting Last July 1** |
| 1. Ensure the Nisqually Indian Tribe has information available for services and support. | At least quarterly DDA and the Nisqually Indian Tribe will schedule a meeting to review the 7.01 Plan.  The local DDA liaison will contact the Nisqually Indian Tribal Representatives and explore and identify the needs of the Nisqually Indian Tribe and attempt to promote local collaboration.  Provide written information about DDA services to the Nisqually Indian Tribe at least annually.  DDA will provide training and/or orientation to the Nisqually Indian Tribe regarding Intake and Eligibility and general information for access to DDA services.  The designated local DDA liaison will participate in meetings as requested by the Nisqually Indian Tribe.  The designated local DDA liaison will participate and attend Nisqually Indian Tribal activities and events such as the Nisqually Indian Tribal Health Fair in August. | The Nisqually Indian Tribal members will have the opportunity to apply and receive services as Tribal member DDA eligibility is identified | DDA Regional Administrator (RA) and DDA Quality Assurance (QA) Manager  Office of Indian Policy (OIP)  Regional Manager  Loni Greninger  DDA local Tribal Liaison Cathleen Corcorran  Tribal Representatives  Will meet in:  April 2014  July 2014  October 2014  January 2015 | DDA and the Nisqually Indian Tribe met on:  February 13, 2014  March 26, 2014 |
| 2. Provide written information about DDA services to the Nisqually Indian Tribe at least annually | In conjunction with Office of Indian Policy, Region 3 DDA will send information on DDA services to the Nisqually Indian Tribal Community Services staff which will include:   * Current brochures describing DDA services; * A current list of Region 3 DDA staff designated as Tribal liaisons, including staff telephone numbers and email addresses.   DDA local Tribal Liaison will set up an informational table at the Tribe (location determined by Tribe) for tribal staff and tribal citizens to stop by and discuss services, eligibility, etc. | Information about DDA services and local contacts will be available to the Nisqually Indian Tribe on an ongoing basis.  Tribal staff and citizens will build a relationship with the local liaison, and will be aware of current DDA services. | DDA Regional QA Manager will provide on an annual basis  DDA Local Tribal Liaison will come to the Tribe every six months, or more often if Tribe invites. | The information identified in section 2 was provided in the 7.01 meeting in February 2014 to the designated Nisqually Indian Tribal members, as well as Office of Indian Policy. |