DSHS 7.01 POLICY PLAN

DEVELOPMENTAL DISABILITIES ADMINISTRATION			REGION 2

| Policy 7.01 Plan and Progress Report Plan Due Dates: April 2 (Regional Plan submitted to Assistant Secretary) and April 30 (Assistant Secretary Plan submitted to IPSS) of each year. Progress Report Due Dates: April 2 (Regional Plan submitted to Assistant Secretary) and April 30 (Assistant Secretary Plan submitted to IPSS) of each year. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Implementation Plan |  |  |  | Progress Report |
| (1) Goals/Objectives | (2) Activities | (3) Expected Outcome | (4) Lead Staff and Target Date | (5) Status Update for the Fiscal Year Starting Last July 1 |
| Attend Regional Tribal Coordinating Council (RTCC), 7.01 meetings and other planning meetings as necessary. | Attend and participate in quarterly meetings. RTCC dates/locations: 3/11/14 – Sauk Suiattle 6/10/14 – To be determined 9/16/14 – DSHS 12/19/1 – To be determined ADSA/DDA 7.01 5/01/14 – Snohomish County AAA 8/07/14 – DDA Everett 11/6/14 – Upper Skagit 2/5/15 – To be determined | Increase communication between Tribes and state government. RTCC is a collaborative, active membership to include but not limited to tribal consultation, the Centennial Accord and Administrative Policy 7.01 | State: Regional Administrator or designee Tribes: Lummi, Nooksack, Upper Skagit, Sauk-Suiattle, Samish, Stillaguamish, Tulalip and Swinomish Muckleshoot Snoqualmie | RTCC are attended by RA or designee. 7.01 meeting are attended by FSA and liaisons. |
| Enhance and maintain communication between Tribes and Region. | All DDA regional trainings will be forwarded to Tribal representative. | Increase information sharing between Tribes and region. Share training and resource information. | Mary Larson or designee to Tim Collins to Tribes | Several training announcements and conference opportunities have been forwarded to Tim Collins, who shares this information with tribal representatives. On-going activity. |
| Recruitment of American Indian (AI) and Alaska Native (AN) employees. | All job announcements will be forwarded to Tim Collins to be forwarded to Tribal contacts. | Increased knowledge of employment opportunities for Tribal members. | State- Mary Larson or designee and Tim Collins | On-going activity. Several job announcements have been forwarded throughout the year. |
| Establish and maintain a working relationship between the region and Native American people. Continue to share pertinent information about DDA services to Tribal members | Outreach liaison will participate in at least one Health Fair each year. Outreach liaison will visit each tribe to introduce them and ensure current eligibility information is given to each tribe. | DDA will participate with information at Health or Resource fairs. Tribal Social Service offices will have up to date information about DDA services. | Leslie Terpstra | Lonnie Ripley is no longer the liaison. Leslie Terpstra is one of the liaisons for R2N. DDA staff has participated in Health and Resource fairs as requested. This goal will continue to the next plan. New goal. Find a replacement for Lonnie. Leslie will visit the Lummi, Nooksack, Upper Skagit and Samish tribes. New staff will visit the Sauk-Suiattle, Stillaguamish, Tulalip and Swinomish tribes. |
| Increase awareness of Developmental Disabilities. | DDA will co-host an Autism training with a regional Tribe. | Increase awareness of clients with Autism, information about this diagnosis and strategies to successfully assist the person in meeting their potential. | Mary Larson | DDA is interested in co-sponsoring a training on Autism with any tribe that is interested. |
| Presentation of DDA services. | DDA eligible clients will tell their stories of how DDA services have impacted and enhanced their lives. | Increased awareness of DDA services | Mary Larson |  |
| Increase awareness of the Tribal culture | DDA will set up activities to celebrate Native American month in November 2014 | Increased knowledge of Tribal culture for DDA staff | Leslie Terpstra |  |
| Attendance at regional LICWAC meetings | Regional liaison to attend as requested as a guest. | DDA will be represented at LIC/WAC meetings. | Theresa Responte, Children’s unit supervisor | Staff is available to attend as requested. Theresa’s contact number is 425-339-1968. |
| Increased knowledge of the 7.01 plan for DDD Case/Resource Managers | Two Policy 7.01 trainings will be set up in Region 2, one in the south end, the other in the North end. As Policy 7.01 trainings are offered, case managers will have the opportunity to attend. | DDD Case/Resource managers will have a better understanding of Policy 7.01. | Leslie Terpstra | 7.01 trainings have occurred in the Region: 1/30/14 in Seattle – 4 DDA staff attended 2/19/14 in Everett – 7 DDA staff attended |
|  | Past History |  |  |  |
| Identify American Indians and Alaska Natives with Developmental Disabilities enrolled with DDA. | Consistently use form 02-590 during the intake process that identifies clients that are tribal members or have tribal affiliation. List of currently eligible Tribal members will be available to each Tribe. | Increase the access of Tribal members to DDA programs and services. Mutual understanding of programs, services, policies and issues that Tribal members or DDA staff may present. AI and AN eligible for enrollment will be identified with correct Tribal affiliation. | Mary Larson Chris Osborn – I&E supervisor | This form was developed last year with the input of R2N tribes; it has had a full year of implementation and is used statewide for all Intake and Eligibility initial applications and reviews. |

| Recruitment of American Indian (AI) and Alaska Native (AN) employees. | Invite HR representatives to the August 7.01 meeting to explain the state application process. | Increase knowledge of the state application process. | Mary Larson | NeoGov presentation occurred at the 8/22/13 meeting. |
| --- | --- | --- | --- | --- |
| Increase awareness of Developmental Disabilities. | DDA will co-host an Autism training with a regional Tribe. | Increase awareness of clients with Autism, information about this diagnosis and strategies to successfully assist the person in meeting their potential. | Mary Larson | Autism training co-hosted by the Tulalip Tribe and DDA occurred on 6/27/13 & 8/12/13. This was a 2 part training by Dr. Travis Thompson on “Behavior Challenges in School Age and Adults With Autism & Related Developmental Disabilities”. |